## ReadMe
Natural England
Project Name: |  | Exemplar Diffuse Water Pollution Plan
Atkins Project Number: |  | 5128377
Atkins Document Title: |  | Final Ant Broads and Marshes DWPP Action Table
Atkins Document Ref: |  | DG017
Version | Date | Status | Description | Author | Checker | Reviewer | Authorised
1 | 2014-04-24 | Draft | Draft Action Plan | CA | DG | HG | HG
2 | 2014-06-10 | Final | Revised following comments from natual England and Environment Agency | CA | DG | HG | HG
Overview
This spreadsheet presents the Actions for the Ant Broads and Marshes DWPP. It is a replicate to that in the report. Having the Action Plan in MS Excel format as well allows for easy editing and searching, as well as recording progress.
Description of each worksheet
Worksheet Name |  |  | Description
Ant DWPP_Action_Plan |  |  | This contains the actions for each water body of the Ant Broads and Marshes SSSI. The action are grouped by Sector or theme (Column C) and also by each water body (columns K to O) for easy reference.

## Ant DWPP_Action_Plan
Ant Broads and Marshes SSSI Diffuse Water Pollution Plan - Action Table | [9 empty] | Ant upstream | East Ruston | Brumstead | Smallburgh | Ant downstream
Scale / location | Investigation / Advice / Scheme / Regulation | Sector | Action Ref No. | Action Title | Action Description | Pollutant(s) the action will tackle | Type of action/measure | How? | Criteria for WB selection | GB105034055710 | GB105034055670 | GB105034050910 | GB105034050890 | GB105034051330 | Who? | When? | Progress as of xxxx (insert date) | Issues/ effectiveness/ learning points
SSSI catchment | Investigation | Agriculture & Land Management | A_DWPP_001 | Review the existing Agri-Environment implementation | Undertake a review of the extent of Agri-environment measures uptake including: where active engagement has been successful; where resource protection measures have been implemented; what extent of the catchment is taking up resource protection options; are these measures being located in the right places relative to the risk (overlay erosion risk map and agricultural risk map) and where there is a known issue (link to water quality monitoring / SAGIS outputs for load concentrations on a sub-catchment level). This will help identify, at a sub-catchment level, a prioritisation plan that is linked to specific pressures in individual water bodies. | Phosphorus and Sediment | Evidence investigation & site specific action plan | Natural England - Review of CSF and Agri Environment | Catchments where agricultural pressures (leading to sediment or phosphate loss) are evident in the source apportionment. In the case of phosphate, where agriculture is contributing >25% of the water body's phosphate load. | N | Y | Y | N | N | Natural England
Specific catchments | Scheme | Agriculture & Land Management | A_DWPP_002 | Re-focused agri-environment priorities | Use the outputs A_DWPP_001 (review of existing agri-environment implementation) to implement advice and schemes that are more targeted to phosphate and sediment reduction in areas where there is an issue (based on evidence) or higher risk (based on available evidence). | Phosphorus and Sediment | Scheme | NE Agri-Environment scheme | Catchments where agricultural pressures (leading to sediment or phosphate loss) are evident in the source apportionment. In the case of phosphate, where agriculture is contributing >25% of the water body's phosphate load. | N | Y | Y | N | N | Natural England
SSSI catchment | Investigation | Rural | A_DWPP_003 | Septic tank risk mapping | Undertake a risk mapping exercise using GIS, sewer network map, and undertake a distance to watercourse assessment to produce risk hot spot map to define areas where the water bodies are at increased risk from septic tanks (location and distance to source assessment). | Phosphorus | Evidence investigation | ? | All sub-catchments within the SSSI catchment should be subject to risk mapping in order to understand where the risk is and further targeting etc. | Y | Y | Y | Y | Y | Environment Agency / Natural England / Water Company
Specific catchments | Advice | Rural | A_DWPP_004 | Action on poor septic tank management / mis connections | Dependent on the outcomes of A_DWPP_003 undertake septic tank risk mapping, take action: for example where poor septic tank management is possibly causing an issue, investigate on site on a case by case basis. Also investigate septic tank issues in the EA’s National Incident Recording System (NIRS) NIRS complaints system | Phosphorus | Advice / Regulatory | EA | Prioritise water bodies where OsWwTWs contribute >25% of phosphate load (marked as Y here). | N | Y | N | Y | N | Environment Agency / Natural England / Water Company
Specific catchments | Advice | Rural | A_DWPP_005 | Septic tank management communications | Depending on the outcomes of A_DWPP_003, formulate material and communications plan to advise people of the importance of good septic tank management. Refer to / use / incorporate / build upon the EA’s standard advice document for householders with private sewage treatment plants | Phosphorus | Advice | EA / NE / Water Company | SAGIS shows OsWwTWs as a recurring issue across the SSSI catchment and therefore this measure should be applied to all water bodies | Y | Y | Y | Y | Y | Environment Agency / Natural England / Water Company
Specific catchments | Investigation | Urban | A_DWPP_006 | Investigation into intermittent discharges affecting the SSSI catchment | Investigate the source of intermittent discharges affecting the SSSI catchment and liaise with appropriate body to address the issues through other non-diffuse mechanisms. NB The EA currently investigates intermittent discharges as recorded through its National Incident Recording System (NIRS) complaints system. | Phosphorus | Investigation / regulatory mechanism | EA | Water bodies where intermittents are responsible for >25% of phosphate load | Y | N | N | N | N | Environment Agency
SSSI catchment | Investigation | Rural | A_DWPP_007 | Road run-off investigations | Undertake a risk mapping exercise using road network, slope and connectivity to water course to understand the relative risks from road run-off. Ground-truth with site visits to verify. | Phosphorus and sediment | Evidence investigation | EA, Local Authority, Highways Agency | Water bodies with a significant urban component in the source apportionment. In this case, water bodies that show >25% of phosphate loading from Urban sources have been targeted as priority. | Y | N | N | N | N | Environment Agency / Natural England
Specific catchments | Scheme | Rural | A_DWPP_008 | Road run-off pathway disruption techniques | Depending on the outcomes of A_DWPP_007 (Road run off risk mapping and investigations) implement pathway disruption techniques so that roads are not channelling rural run-off directly into water courses. | Phosphorus and sediment | Scheme | EA, Local Authority, Highways Agency | TBC (dependent on outcomes of related task A_DWPP_007) | TBC | TBC | TBC | TBC | TBC | EA, Local Authority, Highways Agency
Specific catchments | Investigations | Urban | A_DWPP_009 | Assessment of SUDS potential within the catchment | Investigation into SUDS potential to reduce urban diffuse run off in certain areas of the catchment where urban pressures are present. | Phosphates, sediment, metals | Evidence investigation | EA guidance to local planning initiatives (for new builds) and EA/NE work with Local Authorities to retro fit SUDS where appropriate | Key focus on water bodies where large (>25%) portion of the source apportionment is attributed to urban. These are marked as Y here as they are considered priorities. | Y | N | N | N | N | Natural England (driving), Environment Agency and Local Authorities / Councils etc
SSSI catchment | Policy review | Agriculture & Land Management | A_DWPP_010 | Review of phosphate and sediment reducing measures available through HLS and ELS | Undertake a policy review and understand the further scope for targeting towards resource protection and re-targeting of HLS priorities and measures if required. NB The current form of agri-environment (ELS/HLS) has now come to a close with interim arrangements in place for expiring 2014 classic schemes only. In the meantime conduct a review of existing agreements and their effectiveness, in order to identify the possibility to re-negotiate options if deemed appropriate and if a priority for protected areas. | Phosphates and sediment; with some benefit for other determinants. | Evidence investigation | Defra and Natural England review | TBC | n/a | n/a | n/a | n/a | n/a | Natural England, Defra, Environment Agency
SSSI catchment | Advice | Agriculture & Land Management | A_DWPP_011 | FARMSCOPER 1-2-1s | Farm visits to targeted farms to introduce FARMSCOPER and how it can help plan measures and how much it will cost / save the farmer. This could be prioritised where farmers currently are not engaged or where they are engaged and influential with nearby farms (providing a leading by example type approach). This measure will also provide support to farmers in producing nutrient management plan on a farm level. | Phosphates and sediment as primary focus, with some benefit for nitrates, pesticides. In some cases, additional benefits for biodiversity. | Advice and Scheme | Catchment Sensitive Farming (ECSFDI), Natural England catchment officers and ESS delivery officers | Priority catchments marked here include those where arable or livestock are contributing >25% of phosphate load within the catchment; further prioritisation exercise should be undertaken based on local knowledge, contacts and engagement rates | N | Y | Y | N | N | Natural England
Specific catchments | Schemes | Agriculture & Land Management | A_DWPP_012 | Engagement with the Rivers Trusts to maximise wider benefits | Work with the Rivers Trusts (RT) to review their Catchment Based Approach programme of work to see if there is the potential for multiple-wins, or where key DWPP messages could be delivered through RT-to-farmer engagement. | Phosphates and sediment as primary, with some benefit for nitrates, pesticides. In some cases, additional benefits for biodiversity. | Advice and Scheme | Catchment Based Approach | TBC | TBC | TBC | TBC | TBC | TBC | Natural England and Rivers Trusts / Broads Authority
SSSI catchment | Advice | Agriculture & Land Management | A_DWPP_013 | DWPP Communications Plan | Formulate a brief communications plan for the DWPP that targets farm shows and local events to deliver the DWPP message and outcomes. Also engage agronomists to help reinforce the message through their farm contracts. The overall objective of this measure is to spread the DWPP message and encourage farmers to take ownership of the issue and work alongside NE to help solve the problem. | Phosphates and sediment as primary, with some benefit for nitrates, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery | Farm shows / local communication routes | All catchments selected as this isn't an activity that is specifically tied to water bodies. | Y | Y | Y | Y | Y | Natural England
SSSI catchment | Advice | Agriculture & Land Management | A_DWPP_014 | Engagement with local NFU and CLA representatives | Proactive engagement with the local NFU and CLA to present the evidence base and promote a positive relationship. | Sediment and phosphate | Advice delivery | Meetings / presentations | All catchments | Y | Y | Y | Y | Y | Natural England
SSSI catchment | Monitoring outcomes | Agriculture & Land Management | A_DWPP_015 | Monitoring change in practice | For the annual review report: • Track change in practice by asking the Central Team for the number of advice visits and the uptake of agri-environmental options in the catchment for the reporting year • Report on the progress against each of the actions in the Action Plan | All | Monitoring outcomes and compliance | Through future iterations of the action plan | All catchments | Y | Y | Y | Y | Y | Natural England | Bi-annual update
SSSI catchment | Investigation | Agriculture & Land Management | A_DWPP_016 | Bank erosion investigation | Investigation into sources of phosphate /sediment from bank erosion (as identified by SEPARATE model) through targeted catchment walkovers | Sediment and phosphate | Evidence investigation | Catchment Sensitive Farming (ECSFDI), Natural England catchment officers and ESS delivery officers | All catchments with an agricultural component of the source apportionment in order to determine risk | Y | Y | Y | Y | Y | Natural England / Environment Agency
Specific catchments | Investigation | Agriculture & Land Management | A_DWPP_017 | Understand better the extent of agricultural data suppression | Investigate further the issue of suppressed agricultural data, which included: Smallburgh water body (cereals; horticulture; specialist pigs; dairy; and unclassified) ; Ant (downstream): (Mixed; and unclassified); East Runton Stream: Cereals; Horticulture; Specialist Poultry; Dairy; and Lowland Grazing; and Ant (upstream): Horticulture; Dairy; and Unclassified. | Sediment and phosphate | Evidence investigation |  | All water bodies with suppressed agricultural census data | Y | Y | N | Y | Y | Natural England & Defra
Specific catchments | Advice / Schemes: Arable – General cropping | Agriculture & Land Management | A_DWPP_018 | Arable farming measures for General Cropping farm types - promotion of the "top 5" measures for phosphate reduction | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 4 - Establish cover crops in the autumn; 8 - Cultivate compacted tillage soils; 9 - Cultivate and drill across the slope; 13 - Establish in-field grass buffer strips; 15 - Loosen compacted soil layers in grassland fields | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | All general cropping holdings should eventually be targeted however the priorities set out here are for water bodies that show >25% of phosphate load from arable sector (East Ruston and Brumstead) and / or for which the agri census data shows a high proportion of general cropping (>10 holdings in the water body) (East Ruston, Ant upstream and Ant downstream) | Y | Y | Y | N | Y | NE and landowners
Specific catchments | Advice / Schemes: Livestock – Lowland grazing | Agriculture & Land Management | A_DWPP_019 | Livestock farming measures for Lowland grazing farm type - promotion of the "top 5" measures for phosphate reduction. | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 76 - Fence off rivers and streams from livestock; 35 - Reduce the length of the grazing day/grazing season; 61 - Store solid manure heaps on an impermeable base and collect effluent; 78 - Re-site gateways away from high-risk areas; 39 - Construct troughs with concrete base | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | Catchments where livestock farms are registered; however because grazing regimes changing also select water bodies where livestock farming is contributing >10% phosphates in the source apportionment and where livestock farms are grazing. | N | Y | Y | Y | N | NE and landowners
Specific catchments | Advice / Schemes: Arable – General cropping | Agriculture & Land Management | A_DWPP_020 | Arable farming measures for General Cropping farm types - promotion of the "top 5" measures for sediment reduction | Liaise with farmers within the high priority areas to push top 5 measures for sediment reductions on this farm type: 4 - Establish cover crops in the autumn; 8 - Cultivate compacted tillage soils; 15 - Loosen compacted soil layers in grassland fields; 13 - Establish in-field grass buffer strips; and 9 - Cultivate and drill across the slope. | Sediments as primary, with some benefit for phosphates, nitrates, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | All general cropping holdings should eventually be targeted however the priorities set out here are for water bodies for which the agri census data shows a high proportion of general cropping (>10 holdings in the water body) (East Ruston, Ant upstream and Ant downstream) | Y | Y | N | N | Y | NE and landowners
Specific catchments | Advice / Schemes: Livestock – Lowland grazing | Agriculture & Land Management | A_DWPP_021 | Livestock farming measures for Lowland grazing farm type - promotion of the "top 5" measures for sediment reduction. | Liaise with farmers within the high priority areas to push top 5 measures for sediment reductions on this farm type: 76 - Fence off rivers and streams from livestock; 61 - Store solid manure heaps on impermeable base and collect effluent; 35 - Reduce the length of the grazing day / grazing season; 78 - Re-site gateways away from high-risk areas; and 39 - Construct troughs with concrete base. | Sediments as primary, with some benefit for phosphates, nitrates, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | Catchments where livestock farms are registered and where active grazing takes place. | Y | N | N | N | Y | NE and landowners
Specific catchments | Investigation | Water Industry | A_DWPP_022 | Water Company investigations to reduce phosphorus in discharges | EA and Water Company to investigate potential for reducing phosphorus in wastewater discharges in selected catchments. This could be approached either through improving existing operations or through new infrastructure, although consideration could also be given to catchment management approaches as an alternative, where suitable. There may be measures that water companies can voluntarily undertake downstream of assets (downstream of the final effluent sample point) that could mitigate further the effluent concentrations. | Phosphorus | Investigation / regulatory mechanism | Water Company planning cycle / NEP | Action (in the form of investigations) prioritised here in water bodies where >25% of phosphate load is attributed to STW. | N | N | N | N | Y | Environment Agency | 2015
Specific catchments | Regulatory | Agriculture & Land Management | A_DWPP_023 | Unconsented farm discharges | Identify and remedy unconsented discharges from farms, for example specific farms with poor management practice e.g. Slurry pit / field corner management etc. | Phosphorus and sediment | Regulatory mechanism | EA pollution inspection procedure | Investigations in all agriculturally dominated catchments | N | Y | Y | N | N | Environment Agency
Specific catchments | Regulatory | Urban | A_DWPP_024 | Unconsented urban discharges | Continue to identify and remedy unconsented discharges from the urban environment (for example misconnections) through the WFD and NIRS complaint process. | Phosphorus | Regulatory mechanism | EA pollution inspection procedure | Specific catchments where urban is responsible for significant (>25%) portion of the phosphate load, and / or intermittents sources have been identified in the SAGIS model | Y | N | N | N | N | Environment Agency
Specific catchments | Investigation | Agriculture & Land Management | A_DWPP_025 | Adding to the evidence base | Address knowledge gap for sediment to improve evidence base for sediment: • Collate information to generate baseline of information of sediment pressures for the SSSI • Undertake mapping exercises to identify reaches that suffer from deposited sediment; • Identify any literature studies that quantify sediment movement • Commission assessments in water bodies that have data gaps or uncertainties | Sediment | Investigation / regulatory mechanism | Commission of surveys, and data collection | Data collection in specific water bodies that have information gaps or uncertainties | Y | Y | Y | Y | Y | Natural England, Environment Agency